## Slide 1
Education Analyzer Status Report Week Ending May 09, 2025 Submitted by John Smith May 10, 2025

## Slide 2: Agenda…
Status Overview…
Items Completed in Current Week…
Items In Progress…
Items To Be Started…
Samples of Items Completed This Week…
Issues, Risks, Concerns…
Next Steps…
Personal Reflection…

## Slide 3: Status Overview…
Project Status is Yellow
1.0 Business Understanding Not Completed
  Original Start Date : April 28, 2025, Revised Start Date : N/A, Actual Start Date : April 28, 2025
  Original End Date : May 10, 2025, Revised End Date : N/A, Actual End Date : N/A
Met with Professor Nardi on May 1 to review sections of 1.0 Business Understanding in the CRISP-DM documentation
Anticipate completing Scope Document by May 12
No other major issues

## Slide 4: Items Completed in Current Week…
Project Topic Approved
  Task is GREEN – task 100% complete
  Original Start Date: April 28, 2025; Revised Start Date: n/a; Actual Start Date: April 30, 2025
  Original End Date: May 02, 2025; Revised End Date: n/a; Actual End Date: May 02, 2025
  Approved topic is “Education Analyzer"

## Slide 5: Items In Progress…
1.0 Business Understand document not completed
  Task is Yellow – task 90% complete
  Original Start Date : April 28, 2025, Revised Start Date : N/A, Actual Start Date : April 28, 2025
  Original End Date : May 10, 2025, Revised End Date : N/A, Actual End Date : N/A
  Needed clarification on several items in the 1.0 Business Understanding document
    Met with Professor Nardi on May 1
    Anticipate completing 1.0 Business Understanding on May 12
    Will be working weekend to complete so as not to impact other project deliverables

## Slide 6: Items In Progress…
1.0 Business Understand document not completed
  Task is Yellow – task 90% complete
  Original Start Date : April 28, 2025, Revised Start Date : N/A, Actual Start Date : April 28, 2025
  Original End Date : May 10, 2025, Revised End Date : N/A, Actual End Date : N/A
  Needed clarification on several items in the 1.0 Business Understanding document
    Met with Professor Nardi on May 1
    Anticipate completing 1.0 Business Understanding on May 12
    Will be working weekend to complete so as not to impact other project deliverables
Notice, the Three Items in Bullets Describe WHY the Task is Yellow and What Our Mitigation Plan Is…
In This Case, These Items Would Also Appear in "Next Steps" and/or "Issues, Risks, Concerns"…

## Slide 7: Items to Be Started…
2.0 Data Understanding
  Original Start Date: May 11, 2025; Revised Start Date: n/a; Actual Start Date: n/a
  Original End Date: May 24, 2025; Revised End Date: n/a; Actual End Date: n/a
3.0 Data Preparation
  Original Start Date: May 25, 2025; Revised Start Date: n/a; Actual Start Date: n/a
  Original End Date: June 07, 2025; Revised End Date: n/a; Actual End Date: n/a
Note How You Always Show an Original, Revised, and Actual Date Even If You Have None…Here They Act as Placeholders…

## Slide 8: Sample of Items Completed This Week…
Project Overview section of 1.0 Business Understanding document
This is key to the development of the rest of the system
  The “Education Analyzer" project is intended to help school administrators understand the factors that go into student success in High School and below. It will take into account demographics, gender, family history, student history, and other factors in order to offer suggestions for improving student success. The project includes various visualizations to support this topic.

## Slide 9: Project Issues, Risks, Concerns…
Issues
  Had some problems understanding all items in the 1.0 Business Understanding document
  Held a meeting with Professor Nardi on May 1 to clarify concerns
  Anticipate being back on schedule by May 12
Risks
  None at this time
Concerns
  None at this time

## Slide 10: Next Steps…
Follow up with Professor Nardi to review and verify items in the 1.0 Business Understanding document (May 11)
Complete 1.0 Business Understanding
  Original Start Date : April 28, 2025, Revised Start Date : N/A, Actual Start Date : April 28, 2025
  Original End Date : May 10, 2025, Revised End Date : N/A, Actual End Date : N/A
Begin work on 2.0 Data Understanding
  Original Start Date: May 11, 2025; Revised Start Date: n/a; Actual Start Date: n/a
  Original End Date: May 24, 2025; Revised End Date: n/a; Actual End Date: n/a
Begin work 3.0 Data Preparation
  Original Start Date: May 25, 2025; Revised Start Date: n/a; Actual Start Date: n/a
  Original End Date: June 07, 2025; Revised End Date: n/a; Actual End Date: n/a

## Slide 11: Personal Reflection…
Still getting the hang of writing these status reports. But I love how many notes Professor Nardi gives me every week. They are really helping me. I hope this week there will be no issues in the status report.
After reviewing the Business Understanding document, I was amazed at how many items actually go into determining what will be contained in a project. But the more I thought about it, the more I realized just how much of an impact these items have on what will eventually be developed. I have never been involved in most of those items, so I am looking forward to learning first-hand how they work. And while I am concerned about having to work on so many items that I am unfamiliar with, I know I can always ask Professor Nardi for help, and together we will get this done.

## Slide 12: Thank You!...